## MAVIS
Step # | Activity | Owner | Server | Completion Date/Time | Remarks
1 | Raise GoAnywhere firewall change request with the network/infra team. Source: GoAnywhere servers 10.2.100.4 / 10.2.100.5 / 10.2.102.4. Destination 1: ukpnmvsprds31 port 22 (SSH). Destination 2: ukpnmvsprdb31 port 1525 (Oracle). | nxzen Project Team + nxzen BAU | Network / Infra team | Before cutover | Firewall connectivity is Open as confirmed by Nirmal. Hence this step is marked as complete
2 | Obtain and confirm the email distribution list to be used for GoAnywhere job alert notifications. | nxzen Project Team + nxzen BAU | - | Before cutover
3 | Wait for the Friday overnight batch job to complete successfully before starting any deployment activity. | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | 2026-04-11 10:00 | Do not proceed until batch completion is confirmed.
4 | Confirmation that MPR Publication Report has run | nxzen BAU (Shivendra and Praveen) | BOP | 2026-04-11 10:00 |  | Srikar confirmed
5 | Verify the Saturday load completed successfully | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | 2026-04-11 15:00 | Do not proceed until batch completion is confirmed. | Srikar confirmed
6 | Request Control-M to put the MAVIS eway adapter job on hold so no new files are delivered during the cutover window. Get acknowledgement from the Control-M team before proceeding. | nxzen BAU | ukpnmvsprds31 | 2026-04-11 15:00 | Do not proceed until acknowledgement is received. | Srikar confirmed
7 | Request Control-M to put the Sunday staging job on hold. Get acknowledgement from the Control-M team before proceeding. | nxzen BAU | ukpnmvsprds31 | 2026-04-11 15:00 | Do not proceed until acknowledgement is received. | Srikar confirmed
8 | Ensure that the Staging tables related to D0010 and D0150 are empty | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | 2026-04-11 15:00 |  | Radha Checked - All D0010 & D0150 Staging tables are empty
9 | Take backup of the MAVIS relevant Application database tables: STAGE_D0010_026, STAGE_D0010_027, STAGE_D0010_028, STAGE_D0010_029, STAGE_D0010_030, STAGE_D0010_032, STAGE_D0010_033 STAGE_D0150_08A, STAGE_D0150_288, STAGE_D0150_289, STAGE_D0150_290, STAGE_D0150_291, STAGE_D0150_293, STAGE_D0150_295, STAGE_D0150_296, STAGE_D0150_762, MDQ_ETL_FILE, MDQ_APP_MSG_REF, MDQ_ETL_AUDIT, MDQ_ETL_ERROR, MDQ_ETL_RUN. | nxzen DBA | ukpnmvsprdb31 | 2026-04-11 15:30 |  | Radha Checked
10 | Create/Modify the required validation configuration table (MDQ_ETL_VALIDATION_CONFIG, MDQ_ETL_ERROR, MDQ_ETL_FILE) changes. | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | 2026-04-11 16:00 |  | Done by Radha
11 | Create application database stored procedures and packages. | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | 2026-04-11 16:30 |  | Done by Radha
12 | Run insert scripts for reference data: MDQ_APP_MSG_REF and MDQ_ETL_VALIDATION_CONFIG JSON configuration records for D0010 and D0150. | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | 2026-04-11 17:00 |  | Done by Radha
13 | Compile all modified and new packages and procedures. | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | 2026-04-11 17:30 |  | Done by Radha
14 | Verify all modified and new packages and procedures are in VALID compiled state. (Run a query against USER_OBJECTS to confirm no INVALID objects remain) | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | 2026-04-11 17:30 |  | Done by Radha
15 | Take a backup of all impacted DataStage jobs before making any changes. | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-04-11 16:00 |  | Done by Chary
16 | Create the GoAnywhere pickup folder and trigger file folder on the DataStage server. Paths: /dstage/projects/MAVIS_PROD/inbox_gaw AND /dstage/projects/MAVIS_PROD/gaw_file_trigger Ensure the permissions are the same as inbox/DTC directory where eWay and Datastage read/write) | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-04-11 16:30 |  | Done by Samitha
17 | Deploy updated DataStage jobs | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-04-11 17:00 |  | Done by Chary
18 | Compile all modified DataStage jobs. | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-04-11 17:30 |  | Done by Chary
19 | Verify all modified DataStage jobs are in compiled state with no compile errors. | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-04-11 18:00 |  | Done by Chary
20 | Back up existing .ear files and note the current JMS queue configuration on both eWAY servers before making any changes. | nxzen Project Team + nxzen BAU | UKPNIMIBXPRMQ31, UKPNIMIBXPRMQ32 | 2026-04-11 16:00 |  | Done by Samitha
21 | Regenerate the .ear files on both eWAY production servers and update the MAVIS application, including JMS queue changes for D0010 and D0150 file processing. eWAY should now be configured to deliver D0010 and D0150 files to /dstage/projects/MAVIS_PROD/inbox_gaw instead of the legacy DataStage inbox. Other files should continue to be delivered to the current directories | nxzen Project Team + nxzen BAU | UKPNIMIBXPRMQ31, UKPNIMIBXPRMQ32 | 2026-04-11 16:30 |  | Done by Samitha
22 | Share the updated XML file to Neal and Sinida | nxzen BAU | UKPNIMIBXPRMQ31, UKPNIMIBXPRMQ32 | 2026-04-11 16:30 |  | Samitha Sent a email 17:20
23 | Deploy and configure GoAnywhere production job: source folder = /dstage/projects/MAVIS_PROD/inbox_gaw, Oracle stored procedure call configured, trigger file path = /dstage/projects/MAVIS_PROD/gaw_file_trigger, email alerts set for nxzenincomemanagementsupport@ukpowernetworks.co.uk | nxzen Project Team + nxzen BAU | 10.2.100.4, 10.2.100.5, 10.2.102.4 | 2026-04-11 20:00 |  | Done by Nirmal
24 | Integration test: 1) Move all the files from inbox/DTC to a temporary directory. => Done 2) Place the oldest of the outstanding D0010 and D0150 files (two each) in the inbox_gaw folder for GoAnyWhere to process => Done 3) Place the oldest of the outstanding (non D0010/D0150) in inbox/DTC folder for Datastage to process => Done 4) Trigger Datastage staging job => Done Verify end-to-end: (a) trigger file created in gaw_file_trigger by DataStage, => Done (b) 4 files picked up by GoAnywhere in the order of timestamp, => Done (c) Oracle stored procedure called and data staged in STAGE_ tables, all audit information aptured => Done (d) trigger file deleted by GoAnywhere after processing, => Done (e) all 4 file archived or rejected correctly. => Done (f) Datastage has successfully processed the non D0010/D0150 file placed in inbox/DTC => Done Proceed to the next step only if this test has succeeded. If not, resolve the issue and retry | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-04-11 20:30 |  | Done by Divya
25 | Move the remaining D0010 and D0150 files to /dstage/projects/MAVIS_PROD/inbox_gaw directory | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-04-11 21:00 |  | Done by Chary
26 | Move the remaining non D0010 and D0150 files to inbox/DTC directory (Note: A pragmatic approach to be taken w.r.t number of files to be moved based on the outstanding at that point in time) | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-04-11 21:00 |  | Done by Chary
27 | Restart both eWAY servers to ensure all changes take full effect. | nxzen Project Team + nxzen BAU | UKPNIMIBXPRMQ31, UKPNIMIBXPRMQ32 | 2026-04-11 21:30 |  | Done by Samitha
28 | Validate MAVIS subscriptions and ensure all applications and adapters are running correctly after .ear deployment. | nxzen Project Team + nxzen BAU | UKPNIMIBXPRMQ31, UKPNIMIBXPRMQ32 | 2026-04-11 21:30 |  | Done by Samitha
29 | Request Control-M to release mavis eway adapter | nxzen BAU | ukpnmvsprds31 | 2026-04-11 21:30 |  | Done by Rajesh
30 | Confirm that eWAY is now automatically delivering all new D0010 and D0150 files to the new GoAnywhere pickup folder (/dstage/projects/MAVIS_PROD/inbox_gaw). From this point forward, all D0010 and D0150 files received from the industry will be routed by eWAY directly to the new folder, where the GoAnywhere process will pick them up. All other D-Flow files continue to be delivered to the existing DataStage inbox as before. | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-04-11 22:00 |  | Done by Chary
31 | Trigger Datastage staging job using the backend script (and repeat this once finished as per the current BAU process) | nxzen BAU | ukpnmvsprds31 | 2026-04-11 22:30 |  | Done by Chary
32 | Perform post go-live monitoring. Verify: (1) eWAY is delivering D0010/D0150 files to /dstage/projects/MAVIS_PROD/inbox_gaw. => Done (2) During DataStage staging, trigger file appears in /dstage/projects/MAVIS_PROD/gaw_file_trigger. => Done (3) After staging completes, GoAnywhere deletes the trigger file from /dstage/projects/MAVIS_PROD/gaw_file_trigger. (4) Other DTC files are successfully procesed by Datastage as before | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 11/04/2026 22:30:00 - 12/04/2026 18:00 | If any check fails, escalate immediately to nxzen Project Team.
33 | Request Control-M to release Application load job => Done | nxzen BAU | ukpnmvsprds31 | 2026-04-12 18:30
34 | Application Load kickoff -- confirm the MAVIS application load is processing staged data correctly end-to-end. | nxzen BAU | ukpnmvsprds31 | 2026-04-12 18:30
35 | Comms to Business that the staging related activities are complete and files are being staged correctly | nxzen Project Team |  | 2026-04-12 18:30
36 | Comms to Business that the staged files are processed successfully into the application tables | nxzen Project Team |  | 2026-04-13 10:00
Note on B10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: MDQ_ETL_VALIDATION_CONFIG doesn’t currently exist - created by this release Reply: Done. thanks for pointing out
Note on B11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: What are the other table changes? Reply: @Radha Krishnan (nxzen) please add the details
Note on B16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Which jobs are these? Reply: @Sai Krishna Doppalapudi (nxzen) please add the job names here
Note on B17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This can be done in advance. Need to ensure correct Unix permissions are set on them Reply: Agreed. we can do it early. as it is a quick step, better to put it within the change window so that there are no IS governance challenges
Note on B22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Updated XML file to be provided to Sinida and Neal subsequently Reply: covered as next activity
Note on B27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Likely to be a big backlog of D0010s (10k as at 2/4) and also D0036s (1K as at 2/4) - the latter may not be sensible to move back in full Reply: Point taken. Will take a pragmatic approach based on the outstanding at that point in time
Note on B31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assumes there will have been D0010s/D0150s queued up since 15:00 - hopefully that will be the case! Reply: that's correct, Neal
Note on B32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Will be a good test around the potential volume of D0010s (see comment against step 25) but volumes of other flows (particularly D0036) will impact proposed length of task
Note on B36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not sure you can do this by 20:00, based on what step 33 is supposed to be checking Reply: Good point. We may need 2 comms: 1 to say all staging related changes are done and files are being staged. Second one, at the completion of app load, to say that the staging records were processed successsfully
Note on B37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not sure you can do this by 20:00, based on what step 33 is supposed to be checking Reply: Good point. We may need 2 comms: 1 to say all staging related changes are done and files are being staged. Second one, at the completion of app load, to say that the staging records were processed successsfully

## Rollback Plan
Step # | Activity | Owner | Server | Completion Date/Time | Remarks
1 | Stop all active GoAnywhere jobs immediately to prevent any further D0010 and D0150 files being picked up and processed by the new pipeline And Delete it | nxzen Project Team + nxzen BAU | 10.2.100.4, 10.2.100.5, 10.2.102.4
2 | Request Control-M to put the MAVIS eWAY adapter job back on hold to prevent new D0010 and D0150 files being delivered to any folder during the rollback window. | nxzen BAU | ukpnmvsprds31
3 | Move any D0010 and D0150 files currently sitting in /dstage/projects/MAVIS_PROD/inbox_gaw back to the original DataStage inbox folder (inbox/DTC). This ensures no files are lost and DataStage can process them once restored. | nxzen Project Team + nxzen BAU | ukpnmvsprds31
4 | Check the /dstage/projects/MAVIS_PROD/gaw_file_trigger folder and remove any residual trigger files to prevent DataStage or GoAnywhere triggers after rollback. | nxzen Project Team + nxzen BAU | ukpnmvsprds31
5 | Uncomment the existing path and comment down the new path for D0010 and D0150 flows to the mavis.xml file on both servers | nxzen Project Team + nxzen BAU | UKPNIMIBXPRMQ31, UKPNIMIBXPRMQ32
6 | Regenerate the .ear files on both eWAY production servers and update the MAVIS application along with the JMS queues used for file processing. | nxzen Project Team + nxzen BAU | UKPNIMIBXPRMQ31, UKPNIMIBXPRMQ32
7 | Validate MAVIS subscriptions and ensure all applications,adapters are running correctly. | nxzen Project Team + nxzen BAU | UKPNIMIBXPRMQ31, UKPNIMIBXPRMQ32
8 | Restart both eway servers to ensure all changes take effect. | nxzen Project Team + nxzen BAU | UKPNIMIBXPRMQ31, UKPNIMIBXPRMQ32
9 | Place a few files in the source location and verify that the file is processed and moved to the correct destination | nxzen Project Team + nxzen BAU | ukpnmvsprds31
10 | Restore all impacted DataStage jobs from the backup taken in cutover. This reverts the jobs to their pre-cutover state, removing the inbox_gaw routing and trigger file logic. | nxzen Project Team + nxzen BAU | ukpnmvsprds31
11 | Compile all restored DataStage jobs. | nxzen Project Team + nxzen BAU | ukpnmvsprds31
12 | Verify all restored DataStage jobs are in compiled state with no compile errors. | nxzen Project Team + nxzen BAU | ukpnmvsprds31
13 | Drop the new database packages and tables deployed during cutover: PKG_DTC_VALIDATION, PKG_DTC_D0010, PKG_DTC_D0150, MDQ_ETL_VALIDATION_CONFIG, Also revert the DDL changes made to MDQ_ETL_ERROR and MDQ_ETL_FILE. | nxzen Project Team + nxzen BAU | ukpnmvsprdb31
14 | If any staging table data STAGE_D0010_026, STAGE_D0010_027, STAGE_D0010_028, STAGE_D0010_029, STAGE_D0010_030, STAGE_D0010_032, STAGE_D0010_033 STAGE_D0150_08A, STAGE_D0150_288, STAGE_D0150_289, STAGE_D0150_290, STAGE_D0150_291, STAGE_D0150_293, STAGE_D0150_295, STAGE_D0150_296, STAGE_D0150_762, MDQ_ETL_FILE, MDQ_APP_MSG_REF, MDQ_ETL_AUDIT, MDQ_ETL_ERROR, MDQ_ETL_RUN. was inserted or modified by the new pipeline during the cutover window, restore the affected tables from the backup taken in cutover | nxzen Project Team + nxzen BAU | ukpnmvsprdb31
15 | Verify the database is back to its pre-cutover state. Run a query against USER_OBJECTS to confirm no INVALID or unexpected objects remain. Check MDQ_APP_MSG_REF for any spurious rows inserted during cutover. | nxzen Project Team + nxzen BAU | ukpnmvsprdb31
16 | Move all files moved to inbox_gaw back to inbox/DTC | nxzen Project Team + nxzen BAU | ukpnmvsprds31
17 | Request Control-M to release the MAVIS eWAY adapter job so that eWAY resumes delivering files to the DataStage inbox. | nxzen Project Team + nxzen BAU | ukpnmvsprds31

## Comments
The Control-M job in step 7 needs to be re-enabled presumably? | I spoke to Sai Krishna. Their current approach is manually running Staging. Only on days when the outstanding count is within the manageable limit, they ask for Control-m triggering of Staging job. Hence, I have not included a step for resuming this
Not clear what's happening with the Control-M job for staging - is that just held entirely at the moment because of the backlog? | Yes. Covered in the previous point
What's happening with MHHS staging during this cutover? | Whenever datastage staging is triggered, one parallel thread starts the MHHS staging jobs as well. On a daily basis, support team triggers datastage staging in the morning which in turn triggers the MHHS staging. After that, at regular intervals during the day, they are also triggering it manually.
Just to confirm: there are no Control-M changes required to any of the jobs, because all of the controlling logic is built into the DataStage jobs? | That's correct
Following on from above, please confirm if the BAU team need to be running things differently in future to manage backlogs generally, and if so, that they have suitable knowledge on that | We expect the faster staging process to handle the volume of D0010 and D0150s and no manual intervention may be required. If it is about other DFlows, they can follow the same principle as of today. To manually control D0010 and D0150s, they need to move files to temporary directory and move only the required files
How long is ELS for? | 1 week