## Slide 1
SOFTWARE DEVELOPMENT LIFE CYCLE
Waterfall Methodology
A structured, sequential, phase-gated approach to software delivery
Plan
Design
Build
Test
Deploy
Maintain
Confidential | 2026 | Industry Standard Framework

## Slide 2
Waterfall SDLC — Phase Overview
Sequential, phase-gated delivery model — each phase signed off before the next begins
Waterfall Methodology | Industry Standard SDLC | Confidential
2026
Phase 1
Planning &
Requirements
• BID / Feasibility
• BRD / Use Cases
• Requirements Freeze
• RTM
→
Phase 2
System
Design
• HLD / LLD
• Architecture
• ARB Submission
• Test Strategy
→
Phase 3
Development
& Build
• Coding
• Code Review
• Unit Testing
• Build Artifacts
→
Phase 4
Testing
SIT & UAT
• SIT / Performance
• Security Testing
• Witness Test
• UAT
• UAT Sign-off
→
Phase 5
Deployment
& Go-Live
• CAB Approval
• Cutover Runbook
• Go-Live
• Smoke Test
→
Phase 6
ELS &
Maintenance
• Hypercare (ELS)
• PIR
• BAU Handover
• Project Closure
Gates:
Gate 1: Requirements Sign-off → Gate 2: ARB + Design Approval → Gate 3: Build Complete → Gate 4: SIT Pass + UAT Sign-off → Gate 5: CAB Approval (Go-Live) → Gate 6: ELS Sign-off + BAU Handover
Key Principle: Each phase must be fully completed and formally signed off before the next phase begins. Any changes after Requirements Freeze must go through formal Change Control.

## Slide 3
Phase 1 — Planning & Requirements
Establish project foundation and capture all business needs before design begins
Waterfall Methodology | Industry Standard SDLC | Confidential
2026
Phase 1
KEY ACTIVITIES
Project Initiation
• Business case / BID preparation
• Feasibility study (technical, financial, operational)
• Project charter & stakeholder identification
• Resource planning & cost estimation
Requirements Gathering
• Stakeholder workshops
• BRD (Business Requirements Document)
• FSD (Functional Specification Document)
• Use case documentation
• Non-functional requirements (NFRs)
• RTM baseline
Planning
• Project plan & milestone schedule
• Risk register
• Change control process defined
KEY DOCUMENTS & DELIVERABLES
BID Document
Business case, cost-benefit, ROI analysis
Project Charter
Scope, objectives, sponsor approval
BRD (Business Requirements Doc)
Full functional & non-functional requirements
FSD (Functional Specification)
Detailed functional specifications
Use Cases
Business process flows & scenarios
RTM (Requirements Traceability Matrix)
Risk Register
Project Plan & Milestone Schedule
ENTRY CRITERIA
✔ Business need / opportunity identified
✔ Executive sponsor assigned
✔ Initial budget approved
✔ Key stakeholders identified
EXIT CRITERIA — Gate 1
✔ BRD & FSD reviewed and approved
✔ Requirements signed off by business
✔ RTM baselined
✔ Project plan approved
✔ Risks documented and accepted
✔ Change control process activated

## Slide 4
Phase 2 — System Design
Translate requirements into technical architecture and detailed design blueprints
Waterfall Methodology | Industry Standard SDLC | Confidential
2026
Phase 2
KEY ACTIVITIES
High Level Design (HLD)
• System architecture & component design
• Technology stack selection
• Integration design & data flows
• Infrastructure & hosting design
Low Level Design (LLD)
• Database design (ERD, table definitions)
• API specifications
• Detailed component / module design
• Security design & controls
Governance
• ARB (Architecture Review Board) submission
• ARB presentation & approval
• Test strategy & test environment planning
• Capacity & performance planning
KEY DOCUMENTS & DELIVERABLES
HLD Document
Architecture diagrams, component overview
LLD Document
Detailed technical specifications
ARB Submission Pack
Architecture proposal for governance
Database Design Document
ERD, table / column specs, indexing
Interface Design Document (IDD)
API contracts, integration specs
Security Design Document
Security controls, threat model
Test Strategy
SIT, Witness Test, UAT, performance, security approach
RTM (updated with design traceability)
ENTRY CRITERIA
✔ Gate 1 passed — BRD signed off
✔ RTM baselined
✔ Architects assigned
✔ Dev environment available
EXIT CRITERIA — Gate 2
✔ HLD & LLD reviewed and approved
✔ ARB approval obtained
✔ Security design signed off
✔ Test strategy approved
✔ Test environments provisioned
✔ RTM updated with design traceability

## Slide 5
Phase 3 — Development & Build
Code, review and unit test all components per the approved Low Level Design
Waterfall Methodology | Industry Standard SDLC | Confidential
2026
Phase 3
KEY ACTIVITIES
Development Setup
• Version control branching strategy (Git)
• Coding standards & conventions defined
• CI/CD pipeline setup
Build & Code
• Feature development per LLD
• Database objects (tables, views, procs)
• Integration & API development
• Batch / ETL pipeline development
Quality Assurance
• Code reviews
• Unit testing
• Static code analysis
• Build artifact creation
• Defect tracking & resolution
• Deployment scripts preparation
KEY DOCUMENTS & DELIVERABLES
Source Code
Version-controlled in Git repository
Unit Test Results
Coverage reports, pass / fail logs
Code Review Records
Pull requests, review comments
Build Artifacts
Compiled binaries, packages, scripts
Deployment Scripts
DB migration scripts, release packages
Static Analysis Report
Code quality and security scan results
RTM (updated)
Technical Documentation (runbooks, config guides)
ENTRY CRITERIA
✔ Gate 2 passed — Design approved
✔ ARB approval in place
✔ Dev environment provisioned
✔ Development team assigned
EXIT CRITERIA — Gate 3
✔ All features built per LLD
✔ Code reviews completed
✔ Unit tests passed (coverage met)
✔ No critical / high open defects
✔ Build artifacts deployable
✔ SIT environment ready

## Slide 6
Phase 4 — Testing (SIT & UAT)
Validate the system against requirements through structured, evidence-based testing
Waterfall Methodology | Industry Standard SDLC | Confidential
2026
Phase 4
KEY ACTIVITIES
SIT — System Integration Testing
Purpose:
Verify all integrated components work
together as a complete system
Activities:
• Execute SIT test cases (functional)
• Integration & end-to-end testing
• Performance & load testing
• Security / penetration testing
• Defect logging, triage & retesting
• SIT sign-off by test lead
KEY DOCUMENTS & DELIVERABLES
UAT — User Acceptance Testing
Purpose:
Business validates the system meets
requirements in a real-world scenario
Activities:
• Business executes UAT test scripts
• Test against BRD & use cases
• Business process walkthroughs
• Defect logging & prioritisation
• Regression testing for fixes
• Formal UAT sign-off by business
ENTRY CRITERIA
✔ Gate 3 passed — Build complete
✔ SIT environment provisioned
✔ Test cases written & reviewed
✔ Test data prepared
EXIT CRITERIA — Gate 4
✔ SIT completed & signed off
✔ UAT completed & signed off
✔ No open P1 / P2 defects
✔ Performance benchmarks met
✔ Security testing passed
✔ RTM — 100% requirements covered

## Slide 7
Phase 5 — Deployment & Go-Live
Controlled release to production following formal governance and CAB approval
Waterfall Methodology | Industry Standard SDLC | Confidential
2026
Phase 5
KEY ACTIVITIES
Pre-Deployment
• CAB submission & approval
• Production environment readiness check
• RMAN / database backup
• Rollback plan documented & approved
• Stakeholder communication sent
• Scheduler jobs on hold
Cutover Execution
• Execute cutover runbook step-by-step
• Deploy DB scripts / application
• Configuration changes applied
• Batch jobs released & verified
Post Go-Live
• Smoke testing in production
• Go-live declaration to stakeholders
• Hypercare / ELS period begins
KEY DOCUMENTS & DELIVERABLES
CAB Change Request
Formal request for production change
Cutover Runbook
Step-by-step deployment instructions
Rollback Plan
Reversion steps if go-live fails
Production Backup Evidence
RMAN backup confirmation
Deployment Log
Record of all steps executed & outcomes
Go-Live Communication
Stakeholder notification
Smoke Test Results
Release Notes — summary of changes deployed
ENTRY CRITERIA
✔ Gate 4 passed — UAT signed off
✔ CAB approval granted
✔ Production backup taken
✔ Rollback plan approved
EXIT CRITERIA — Gate 5
✔ All deployment steps completed
✔ Smoke tests passed in production
✔ Batch jobs released & running
✔ No critical production incidents
✔ Stakeholders notified of go-live
✔ Deployment log completed & filed

## Slide 8
Phase 6 — ELS, BAU & Project Closure
Stabilise the system, transition to operations, and formally close the project
Waterfall Methodology | Industry Standard SDLC | Confidential
2026
Phase 6
KEY ACTIVITIES
ELS — Early Life Support (Hypercare)
What is ELS?
Heightened support period immediately
after go-live (typically 2-4 weeks)
Activities:
• Extended-hours or 24/7 monitoring
• Batch job monitoring & verification
• Incident triage & rapid response
• Performance monitoring
• Daily ELS status reports
• Critical defect fixes (fast-track CAB)
• ELS sign-off when system is stable
KEY DOCUMENTS & DELIVERABLES
BAU Handover & Project Closure
BAU Transition:
• Knowledge transfer to BAU / ops team
• Runbooks & SOPs handed over
• Support model defined (L1/L2/L3)
• On-call rota established
• Monitoring & alerting configured
Post Implementation Review (PIR):
• Lessons learned workshop
• Benefits realisation assessment
• PIR report submitted to PMO
• Formal project closure sign-off
ENTRY CRITERIA
✔ Gate 5 passed — Go-live complete
✔ System live in production
✔ Support team briefed
✔ Monitoring tools active
EXIT CRITERIA — Gate 6
✔ ELS sign-off obtained
✔ BAU team fully transitioned
✔ PIR report completed
✔ Change request closed
✔ Lessons learned documented
✔ Sponsor project closure sign-off

## Slide 9
Key Documents, Gates & Governance
Summary of deliverables, approval gates and governance bodies across all phases
Waterfall Methodology | Industry Standard SDLC | Confidential
2026
KEY DOCUMENTS BY PHASE
Phase 1 — Requirements
BID • Project Charter • BRD • FSD • Use Cases • RTM • Risk Register • Project Plan
Phase 2 — Design
HLD • LLD • ARB Submission • DB Design • IDD • Security Design • Test Strategy
Phase 3 — Development
Source Code • Unit Test Results • Code Review Records • Build Artifacts • Deploy Scripts
Phase 4 — Testing
SIT Test Plan • SIT Results • UAT Test Scripts • Defect Log • UAT Sign-off Certificate
Phase 5 — Deployment
CAB Change Request • Cutover Runbook • Rollback Plan • Deployment Log • Release Notes
Phase 6 — ELS/BAU
ELS Status Reports • ELS Sign-off • BAU Runbooks • PIR Report • Project Closure Report
GOVERNANCE BODIES
ARB
Architecture Review Board
Reviews & approves technical architecture before development begins
CAB
Change Advisory Board
Reviews & approves all production changes before deployment
PMO
Project Management Office
Oversees project governance, reporting and milestone tracking
SC
Steering Committee
Executive oversight, budget approval and escalation resolution
CCB
Change Control Board
Manages post-freeze requirement changes and impact assessment

## Slide 10
Roles & Responsibilities
Key stakeholders and their involvement across the Waterfall lifecycle
Waterfall Methodology | Industry Standard SDLC | Confidential
2026
Executive Sponsor
Approves BID & budget, provides strategic direction, resolves escalations, signs off project closure
Project Manager
Manages plan, budget, risks and issues. Drives phase gates, stakeholder communications and reporting
Business Analyst
Leads requirements gathering, produces BRD, FSD, Use Cases, RTM. Supports UAT
Solution Architect
Produces HLD/LLD, presents ARB submission, governs technical design decisions
Development Team
Builds all components per LLD, conducts code reviews, unit testing, prepares deployment artefacts
Test Team
Writes and executes SIT test cases, manages defect log, signs off SIT completion
Business Users
Executes UAT test scripts, raises defects, provides formal UAT sign-off
Security Team
Reviews security design, conducts penetration testing, signs off security clearance
Infrastructure/DBA
Provisions environments, manages database, supports backup/restore and production deployment
Change Manager
Manages change control, coordinates CAB submissions, handles post-freeze change requests
BAU / Support Team
Participates in ELS, receives knowledge transfer, owns operational support post-handover