## MAVIS
Step # | Activity | Owner | Server | Completion Date/Time | Remarks
1 | Request control-m to put the relevant jobs on hold | nxzen BAU | ukpnmvsprds31 | 2026-04-10 20:00
2 | Wait for Friday overnight batch job to complete | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | 2026-04-11 10:00
3 | Confirmation that MPR Publication Report has run | nxzen BAU (Shivendra & Praveen) | BOP | 2026-04-11 10:00
4 | Verify the Saturday load completed | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | 2026-04-11 10:00
5 | Take RMAN backup of the Mavis App and Datamart databases | nxzen DBA | ukpnmvsprdb31, ukpnmvsprdm31 | 11/04/2026 10:00 - 11/04/2026 14:00
6 | Create/Modify the required Application database Validation config and other table changes | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | 2026-04-11 10:00
7 | Create Application database views, stored procedures And Packages | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | 2026-04-11 11:00
8 | Insert scripts for Reference data (MDQ_APP_MSG_REF) and MDQ_ETL_VALIDATION_Config | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | 2026-04-11 11:30
9 | Compile all the modified/New Packages and Procedures | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | 2026-04-11 12:00
10 | Verify the modified/New Packages and procedures are in compiled state | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | 2026-04-11 12:30
11 | Add the folder exception path /dstage/projects/MAVIS_PROD/inbox_gaw and Trigger file folder for D0010 and D0150 flows to the mavis.xml file on both eway servers: | nxzen Project Team + nxzen BAU | UKPNIMIBXPRMQ31 & UKPNIMIBXPRMQ32 | 2026-04-11 10:00
12 | GoAnywhere Firewall open Source - GoAnywhere Servers : 10.2.100.4, 10.2.100.5, 10.2.102.4 Destination1 Port :22 Destination1. datastage server : ukpnmvsprds31 Destination2 Port :1525 Destination2. databse server : ukpnmvsprdb31 | nxzen Project Team + nxzen BAU | 10.2.100.4, 10.2.100.5, 10.2.102.4
13 | Verify the datastage Trigger file folder, inbox, archive and rejected folders are in place | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-04-11 10:00
14 | Test the GoAnywhere connectivity | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-04-11 11:00
15 | Get the Email list | nxzen Project Team + nxzen BAU | ukpnmvsprds31
16 | GoAnywhere job Setup including email configuration | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-04-11 14:00
17 | Regenerate the .ear files on both eWAY production servers and update the MAVIS application along with the JMS queues used for file processing. | nxzen Project Team + nxzen BAU | UKPNIMIBXPRMQ31 & UKPNIMIBXPRMQ32 | 2026-04-11 10:00
18 | Validate MAVIS subscriptions and ensure all applications,adapters are running correctly. | nxzen Project Team + nxzen BAU | UKPNIMIBXPRMQ31 & UKPNIMIBXPRMQ32 | 2026-04-11 11:00
19 | Restart both eway servers to ensure all changes take effect. | nxzen Project Team + nxzen BAU | UKPNIMIBXPRMQ31 & UKPNIMIBXPRMQ32 | 2026-04-11 12:00
20 | Place a sample test file in the source location and verify that The file is processed and moved to the correct destination | nxzen Project Team + nxzen BAU | UKPNIMIBXPRMQ31 & UKPNIMIBXPRMQ32 | 2026-04-11 14:00
21 | Eway will deliver D0010 and D0150 files to the new folder path /dstage/projects/MAVIS_PROD/inbox_gaw, from which the GoAnywhere process will pick up and process the files. | nxzen Project Team + nxzen BAU | ukpnmvsprds31
22 | Take backup of the impacted datastage jobs | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-04-11 10:00
23 | Deploy Datastage jobs | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-04-11 11:00
24 | Create the Trigger file forlder for D0010 & D0150 , Path : /dstage/projects/MAVIS_DEV_MHHS/gaw_file_trigger | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-04-11 12:30
25 | Compile all the modified jobs | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-04-11 14:00
26 | Verify the modified jobs are in compiled state | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-04-11 14:00
27 | Checkpoint email to Business that the application is ready for business PAT | nxzen Project Team |  | 2026-04-11 17:00
28 | PAT by business stakeholders | Peter/Neal/Sinida |  | 2026-04-11 17:00
29 | Confirmation from business that the PAT is complete | Peter/Neal/Sinida |  | 2026-04-11 17:00
30 | Request Control-M to release staging load job on Saturday after UC018 completion | nxzen BAU | ukpnmvsprds31
31 | Sanity check to ensure staging loads are working fine 1. Eway send file to this Path : /dstage/projects/MAVIS_PROD/inbox_gaw 2. During the Datastage staging execution, need to verify the trigger file on this Path : /dstage/projects/MAVIS_DEV_MHHS/gaw_file_trigger 3. End of D0010 & D0150 staging process verify Goanywhere Deleting the trigger file or not from this Path : /dstage/projects/MAVIS_DEV_MHHS/gaw_file_trigger | nxzen BAU |  | 11/04/2026 15:00:00 - 11/04/2026 16:30
32 | Request control-m to put Saturday UC018 job on hold | nxzen BAU | ukpnmvsprds31
33 | Request control-m to release Saturday UC018 job | nxzen BAU | ukpnmvsprds31
34 | Staging Load kickoff | nxzen BAU | ukpnmvsprds31
34 | App Load kickoff | nxzen BAU | ukpnmvsprds31