## Cutover Plan
MAVIS Faster Staging ¦ Cutover Plan v0.2 ¦ Cutover Date: Saturday 11 April 2026 ¦ Window: 10/04/2026 20:00 to 11/04/2026 17:00
Step # | Phase | Activity | Owner | Server / Target | Target Date / Time | Remarks | Status | Sign-off
PRE-CUTOVER CHECKLIST -- All items below must be completed BEFORE Cutover Day
PC-1 | Pre-Cutover | Raise GoAnywhere firewall change request with the network/infra team. Source: GoAnywhere servers 10.2.100.4 / 10.2.100.5 / 10.2.102.4. Destination 1: ukpnmvsprds31 port 22 (SSH). Destination 2: ukpnmvsprdb31 port 1525 (Oracle). | nxzen Project Team + nxzen BAU | Network / Infra team | At least 5 business days before cutover | Firewall approvals require lead time. Do NOT leave this for cutover day.
PC-2 | Pre-Cutover | Obtain and confirm the email distribution list to be used for GoAnywhere job alert notifications. | nxzen Project Team + nxzen BAU | -- | At least 2 business days before cutover | Required for GoAnywhere job configuration (Step 22).
PC-3 | Pre-Cutover | Prepare and review GoAnywhere job configuration (source folder, Oracle stored procedure call, trigger file path, email alerts) in a non-prod environment before cutover day. | nxzen Project Team + nxzen BAU | GoAnywhere non-prod | At least 2 business days before cutover | Config must be tested end-to-end in non-prod before production deployment.
PC-4 | Pre-Cutover | Confirm RMAN backup schedule and resource availability with the DBA team. Window: 11/04/2026 10:00 to 14:00 on ukpnmvsprdb31 and ukpnmvsprdm31. | nxzen DBA | ukpnmvsprdb31, ukpnmvsprdm31 | At least 2 business days before cutover
PC-5 | Pre-Cutover | Confirm PAT participants (Peter Waymont / Neal Medley / Sinida) are available on Saturday 11/04/2026 from 17:00. | nxzen Project Team | -- | At least 2 business days before cutover
PHASE 1 -- PREPARATION ¦ Friday 10 April 2026
1 | Phase 1 -- Preparation | Request Control-M to put the D0010 and D0150 staging jobs on hold so no new files are picked up during the cutover window. Obtain written acknowledgement from the Control-M team before proceeding. | nxzen BAU | ukpnmvsprds31 | 2026-10-04 20:00 | Do not proceed until acknowledgement is received.
PHASE 2 -- VERIFICATION AND BACKUP ¦ Saturday 11 April 2026 ¦ Do NOT proceed to deployment until each step is confirmed
2 | Phase 2 -- Verification | Wait for the Friday overnight batch job to complete successfully before starting any deployment activity. | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | 2026-11-04 10:00 | Do not proceed until batch completion is confirmed.
3 | Phase 2 -- Verification | Confirm that the MPR (Meter Point Registration) Publication Report has run and completed successfully. | nxzen BAU (Shivendra and Praveen) | BOP | 2026-11-04 10:00 | Obtain written confirmation.
4 | Phase 2 -- Verification | Verify the Saturday load completed successfully -- check row counts and error logs. | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | 2026-11-04 10:00
5 | Phase 2 -- RMAN Backup | Take RMAN hot backup of the MAVIS Application database and Datamart database. | nxzen DBA | ukpnmvsprdb31, ukpnmvsprdm31 | 11/04/2026 10:00 to 14:00 | RMAN runs as a hot (online) backup -- Phases 3, 4 and 5 may run in parallel during this window. Do NOT start Phase 6 (GoAnywhere) until backup is confirmed complete.
PHASE 3 -- DATABASE DEPLOYMENT ¦ Can run in parallel with Phases 4 and 5 during RMAN backup window
6 | Phase 3 -- DB | Create/Modify the required validation configuration table (MDQ_ETL_VALIDATION_CONFIG) and any other table-level changes (e.g. new columns, constraints). | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | 2026-11-04 10:00
7 | Phase 3 -- DB | Create application database views, stored procedures and packages: PKG_DTC_VALIDATION, PKG_DTC_D0010, PKG_DTC_D0150. | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | 2026-11-04 11:00
8 | Phase 3 -- DB | Run insert scripts for reference data: MDQ_APP_MSG_REF and MDQ_ETL_VALIDATION_CONFIG JSON configuration records for D0010 and D0150. | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | 2026-11-04 11:30
9 | Phase 3 -- DB | Compile all modified and new packages and procedures in the MAVIS application schema. | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | 2026-11-04 12:00
10 | Phase 3 -- DB | Verify all modified and new packages and procedures are in VALID compiled state. Run a query against USER_OBJECTS to confirm no INVALID objects remain. | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | 2026-11-04 12:30 | Abort and raise issue immediately if any objects remain INVALID.
PHASE 4 -- DATASTAGE DEPLOYMENT ¦ Can run in parallel with Phases 3 and 5 during RMAN backup window
11 | Phase 4 -- DataStage | Take a backup of all impacted DataStage jobs before making any changes. Export job definitions as a rollback safety net. | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-11-04 10:00 | Required as rollback point.
12 | Phase 4 -- DataStage | Verify the existing DataStage folder structure is in place: inbox, archive and rejected folders for D0010 and D0150. | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-11-04 10:00
13 | Phase 4 -- DataStage | Create the GoAnywhere pickup folder and trigger file folder on the DataStage server. Paths: /dstage/projects/MAVIS_PROD/inbox_gaw AND /dstage/projects/MAVIS_PROD/gaw_file_trigger | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-11-04 10:30 | IMPORTANT: Use MAVIS_PROD -- NOT MAVIS_DEV_MHHS. Ensure correct UNIX permissions so both DataStage and GoAnywhere processes can read and write.
14 | Phase 4 -- DataStage | Deploy updated DataStage jobs -- route D0010 and D0150 files to inbox_gaw and write a 1-byte trigger file to gaw_file_trigger on staging completion. | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-11-04 11:00
15 | Phase 4 -- DataStage | Compile all modified DataStage jobs. | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-11-04 12:30
16 | Phase 4 -- DataStage | Verify all modified DataStage jobs are in compiled state with no compile errors. | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-11-04 13:00
PHASE 5 -- eWAY DEPLOYMENT ¦ Can run in parallel with Phases 3 and 4 during RMAN backup window
17 | Phase 5 -- eWAY | Back up existing .ear files and note the current JMS queue configuration on both eWAY servers before making any changes. | nxzen Project Team + nxzen BAU | UKPNIMIBXPRMQ31, UKPNIMIBXPRMQ32 | 2026-11-04 10:00 | Required as rollback point.
18 | Phase 5 -- eWAY | Regenerate the .ear files on both eWAY production servers and update the MAVIS application, including JMS queue changes for D0010 and D0150 file processing. eWAY will now deliver files to /dstage/projects/MAVIS_PROD/inbox_gaw instead of the legacy DataStage inbox. | nxzen Project Team + nxzen BAU | UKPNIMIBXPRMQ31, UKPNIMIBXPRMQ32 | 2026-11-04 10:30
19 | Phase 5 -- eWAY | Validate MAVIS subscriptions and ensure all applications and adapters are running correctly after .ear deployment. | nxzen Project Team + nxzen BAU | UKPNIMIBXPRMQ31, UKPNIMIBXPRMQ32 | 2026-11-04 11:00
20 | Phase 5 -- eWAY | Restart both eWAY servers to ensure all changes take full effect. | nxzen Project Team + nxzen BAU | UKPNIMIBXPRMQ31, UKPNIMIBXPRMQ32 | 2026-11-04 12:00 | Coordinate restart to avoid simultaneous downtime on both nodes.
20A | Phase 5 -- eWAY | Confirm that eWAY is now automatically delivering all new D0010 and D0150 files to the new GoAnywhere pickup folder (/dstage/projects/MAVIS_PROD/inbox_gaw). No manual file movement is required. From this point forward, all D0010 and D0150 files received from the industry will be routed by eWAY directly to the new folder, where the GoAnywhere process will pick them up. All other D-Flow files continue to be delivered to the existing DataStage inbox as before. | nxzen Project Team + nxzen BAU | UKPNIMIBXPRMQ31, UKPNIMIBXPRMQ32 | 2026-11-04 12:30 | Verify by checking eWAY routing configuration and confirming no D0010/D0150 traffic is still pointing to the old folder. This is a confirmation checkpoint -- no action needed if Steps 18-20 completed successfully.
PHASE 6 -- GOANYWHERE SETUP AND END-TO-END TEST ¦ Start only after RMAN backup is confirmed complete (~14:00)
21 | Phase 6 -- GoAnywhere | Confirm GoAnywhere firewall rules are active. Test SSH (port 22) connectivity to ukpnmvsprds31 and Oracle (port 1525) connectivity to ukpnmvsprdb31 from all three GoAnywhere servers (10.2.100.4, 10.2.100.5, 10.2.102.4). | nxzen Project Team + nxzen BAU | 10.2.100.4, 10.2.100.5, 10.2.102.4 | 2026-11-04 14:00 | Firewall request must have been raised pre-cutover (PC-1). Raise a P1 incident if connectivity fails.
22 | Phase 6 -- GoAnywhere | Configure GoAnywhere production job: source folder = /dstage/projects/MAVIS_PROD/inbox_gaw, Oracle stored procedure call configured, trigger file path = /dstage/projects/MAVIS_PROD/gaw_file_trigger, email alerts set using the approved distribution list (PC-2). | nxzen Project Team + nxzen BAU | 10.2.100.4, 10.2.100.5, 10.2.102.4 | 2026-11-04 14:00
23 | Phase 6 -- GoAnywhere | Place a sample D0010 and D0150 test file in the source folder and verify end-to-end: (a) file picked up by GoAnywhere, (b) Oracle stored procedure called and data staged in STAGE_ tables, (c) trigger file created in gaw_file_trigger by DataStage, (d) trigger file deleted by GoAnywhere after processing, (e) file archived or rejected correctly. | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-11-04 14:30 | Validates the full end-to-end pipeline before handing over to business for PAT.
PHASE 7 -- BUSINESS PAT (User Acceptance Testing)
24 | Phase 7 -- PAT | Send a checkpoint email to business stakeholders confirming the application is ready for PAT. Include a summary of what was deployed and what to test. | nxzen Project Team | -- | 2026-11-04 17:00
25 | Phase 7 -- PAT | Business stakeholders perform PAT -- validate that D0010 and D0150 data is accessible and accurate in MAVIS. | Peter Waymont / Neal Medley / Sinida | -- | 2026-11-04 17:00 | Business to follow the agreed PAT test script.
26 | Phase 7 -- PAT | Receive written sign-off from business stakeholders confirming PAT is complete and go-live is approved. | Peter Waymont / Neal Medley / Sinida | -- | 2026-11-04 17:00 | DO NOT proceed to Phase 8 without written sign-off.
PHASE 8 -- GO-LIVE ¦ Only after PAT sign-off is received from business
27 | Phase 8 -- Go-Live | Request Control-M to put the Saturday UC018 job on hold -- prevents the legacy DataStage staging job from running while the new GoAnywhere / stored procedure pipeline is being activated. | nxzen BAU | ukpnmvsprds31 | After PAT sign-off
28 | Phase 8 -- Go-Live | Request Control-M to release the D0010 and D0150 staging load job so GoAnywhere can begin processing live files after UC018 completes. | nxzen BAU | ukpnmvsprds31 | After Step 27
29 | Phase 8 -- Go-Live | Perform go-live sanity check. Verify: (1) eWAY is delivering files to /dstage/projects/MAVIS_PROD/inbox_gaw. (2) During DataStage staging, trigger file appears in /dstage/projects/MAVIS_PROD/gaw_file_trigger. (3) After staging completes, GoAnywhere deletes the trigger file from /dstage/projects/MAVIS_PROD/gaw_file_trigger. | nxzen BAU | ukpnmvsprds31 | 11/04/2026 15:00 to 16:30 | If any check fails, escalate immediately to nxzen Project Team.
30 | Phase 8 -- Go-Live | Request Control-M to release the Saturday UC018 job once the go-live sanity check is confirmed successful. | nxzen BAU | ukpnmvsprds31 | After Step 29 confirmed
31 | Phase 8 -- Go-Live | Staging Load kickoff -- confirm the first live batch of D0010 and D0150 files is being processed by the new GoAnywhere / stored procedure pipeline. | nxzen BAU | ukpnmvsprds31 | After Step 30
32 | Phase 8 -- Go-Live | Application Load kickoff -- confirm the MAVIS application load is processing staged data correctly end-to-end. | nxzen BAU | ukpnmvsprds31 | After Step 31
ROLLBACK PLAN -- Activate only if a critical failure cannot be resolved within the cutover window
RB-1 | Rollback | Restore RMAN backup of the MAVIS Application and Datamart databases (taken in Step 5). | nxzen DBA | ukpnmvsprdb31, ukpnmvsprdm31 | As required
RB-2 | Rollback | Restore DataStage jobs from the backup taken in Step 11. | nxzen Project Team | ukpnmvsprds31 | As required
RB-3 | Rollback | Restore eWAY .ear files from the backup taken in Step 17. Restart both eWAY servers. | nxzen Project Team | UKPNIMIBXPRMQ31, UKPNIMIBXPRMQ32 | As required
RB-4 | Rollback | Request Control-M to re-enable the original DataStage staging jobs for D0010 and D0150. | nxzen BAU | ukpnmvsprds31 | As required
RB-5 | Rollback | Communicate the rollback to business stakeholders and agree the next available cutover window. | nxzen Project Team | -- | As required