## Cutover_Activites
Step # | Activity | Owner | Server | Completion Date/Time | Remarks
1 | Raise GoAnywhere firewall change request with the network/infra team. Source: GoAnywhere servers 10.2.100.4 / 10.2.100.5 / 10.2.102.4. Destination 1: ukpnmvsprds31 port 22 (SSH). Destination 2: ukpnmvsprdb31 port 1525 (Oracle). | nxzen Project Team + nxzen BAU | Network / Infra team | Before cutover | Firewall connectivity is Open as confirmed by Nirmal. Hence this step is marked as complete
2 | Obtain and confirm the email distribution list to be used for GoAnywhere job alert notifications. | nxzen Project Team + nxzen BAU | - | Before cutover
3 | Wait for the Friday overnight batch job to complete successfully before starting any deployment activity. | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | 2026-11-04 10:00 | Do not proceed until batch completion is confirmed.
4 | Confirmation that MPR Publication Report has run | nxzen BAU (Shivendra and Praveen) | BOP | 2026-11-04 10:00
5 | Verify the Saturday load completed successfully | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | 2026-11-04 15:00 | Do not proceed until batch completion is confirmed.
6 | Request Control-M to put the MAVIS eway adapter job on hold so no new files are delivered during the cutover window. Get acknowledgement from the Control-M team before proceeding. | nxzen BAU | ukpnmvsprds31 | 2026-11-04 15:00 | Do not proceed until acknowledgement is received.
7 | Request Control-M to put the Sunday staging job on hold. Get acknowledgement from the Control-M team before proceeding. | nxzen BAU | ukpnmvsprds31 | 2026-11-04 15:00 | Do not proceed until acknowledgement is received.
8 | Ensure that the Staging tables related to D0010 and D0150 are empty | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | 2026-11-04 15:00
9 | Take backup of the MAVIS relevant Application database tables: | nxzen DBA | ukpnmvsprdb31 | 2026-11-04 15:30
STAGE_D0010_026, STAGE_D0010_027, STAGE_D0010_028, STAGE_D0010_029, STAGE_D0010_030, STAGE_D0010_032, STAGE_D0010_033
STAGE_D0150_08A, STAGE_D0150_288, STAGE_D0150_289, STAGE_D0150_290, STAGE_D0150_291, STAGE_D0150_293, STAGE_D0150_295, STAGE_D0150_296, STAGE_D0150_762,
MDQ_ETL_FILE, MDQ_APP_MSG_REF, MDQ_ETL_AUDIT, MDQ_ETL_ERROR, MDQ_ETL_RUN.
10 | Create/Modify the required validation configuration table (MDQ_ETL_VALIDATION_CONFIG, MDQ_ETL_ERROR, MDQ_ETL_FILE changes. | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | 2026-11-04 16:00
11 | Create application database stored procedures and packages. | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | 2026-11-04 16:30
12 | Run insert scripts for reference data: MDQ_APP_MSG_REF and MDQ_ETL_VALIDATION_CONFIG JSON configuration records for D0010 and D0150. | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | 2026-11-04 17:00
13 | Compile all modified and new packages and procedures. | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | 2026-11-04 17:30
14 | Verify all modified and new packages and procedures are in VALID compiled state. | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | 2026-11-04 17:30
(Run a query against USER_OBJECTS to confirm no INVALID objects remain)
15 | Take a backup of all impacted DataStage jobs before making any changes. | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-11-04 16:00
16 | Create the GoAnywhere pickup folder and trigger file folder on the DataStage server. Paths: /dstage/projects/MAVIS_PROD/inbox_gaw AND /dstage/projects/MAVIS_PROD/gaw_file_trigger | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-11-04 16:30
Ensure the permissions are the same as inbox/DTC directory where eWay and Datastage read/write)
17 | Deploy updated DataStage jobs | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-11-04 17:00
18 | Compile all modified DataStage jobs. | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-11-04 17:30
19 | Verify all modified DataStage jobs are in compiled state with no compile errors. | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-11-04 18:00
20 | Back up existing .ear files and note the current JMS queue configuration on both eWAY servers before making any changes. | nxzen Project Team + nxzen BAU | UKPNIMIBXPRMQ31, | 2026-11-04 16:00
UKPNIMIBXPRMQ32
21 | Regenerate the .ear files on both eWAY production servers and update the MAVIS application, including JMS queue changes for D0010 and D0150 file processing. eWAY should now be configured to deliver D0010 and D0150 files to /dstage/projects/MAVIS_PROD/inbox_gaw instead of the legacy DataStage inbox. Other files should continue to be delivered to the current directories | nxzen Project Team + nxzen BAU | UKPNIMIBXPRMQ31, | 2026-11-04 16:30
UKPNIMIBXPRMQ32
22 | Share the updated XML file to Neal and Sinida | nxzen BAU | UKPNIMIBXPRMQ31, | 2026-11-04 16:30
UKPNIMIBXPRMQ32
23 | Deploy and configure GoAnywhere production job: source folder = /dstage/projects/MAVIS_PROD/inbox_gaw, Oracle stored procedure call configured, trigger file path = /dstage/projects/MAVIS_PROD/gaw_file_trigger, email alerts set for nxzenincomemanagementsupport@ukpowernetworks.co.uk | nxzen Project Team + nxzen BAU | 10.2.100.4, | 2026-11-04 20:00
10.2.100.5,
10.2.102.4
24 | Integration test: | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-11-04 20:30
1) Move all the files from inbox/DTC to a temporary directory.
2) Place the oldest of the outstanding D0010 and D0150 files (two each) in the inbox_gaw folder for GoAnyWhere to process
3) Place the oldest of the outstanding (non D0010/D0150) in inbox/DTC folder for Datastage to process
4) Trigger Datastage staging job
Verify end-to-end:
(a) trigger file created in gaw_file_trigger by DataStage,
(b) 4 files picked up by GoAnywhere in the order of timestamp,
(c) Oracle stored procedure called and data staged in STAGE_ tables, all audit information aptured
(d) trigger file deleted by GoAnywhere after processing,
(e) all 4 file archived or rejected correctly.
(f) Datastage has successfully processed the non D0010/D0150 file placed in inbox/DTC
Proceed to the next step only if this test has succeeded. If not, resolve the issue and retry
25 | Move the remaining D0010 and D0150 files to /dstage/projects/MAVIS_PROD/inbox_gaw directory | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-11-04 21:00
26 | Move the remaining non D0010 and D0150 files to inbox/DTC directory (Note: A pragmatic approach to be taken w.r.t number of files to be moved based on the outstanding at that point in time) | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-11-04 21:00
27 | Restart both eWAY servers to ensure all changes take full effect. | nxzen Project Team + nxzen BAU | UKPNIMIBXPRMQ31, | 2026-11-04 21:30
UKPNIMIBXPRMQ32
28 | Validate MAVIS subscriptions and ensure all applications and adapters are running correctly after .ear deployment. | nxzen Project Team + nxzen BAU | UKPNIMIBXPRMQ31, | 2026-11-04 21:30
UKPNIMIBXPRMQ32
29 | Request Control-M to release mavis eway adapter | nxzen BAU | ukpnmvsprds31 | 2026-11-04 21:30
30 | Confirm that eWAY is now automatically delivering all new D0010 and D0150 files to the new GoAnywhere pickup folder (/dstage/projects/MAVIS_PROD/inbox_gaw). From this point forward, all D0010 and D0150 files received from the industry will be routed by eWAY directly to the new folder, where the GoAnywhere process will pick them up. All other D-Flow files continue to be delivered to the existing DataStage inbox as before. | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 2026-11-04 22:00
31 | Trigger Datastage staging job using the backend script (and repeat this once finished as per the current BAU process) | nxzen BAU | ukpnmvsprds31 | 2026-11-04 22:30
32 | Perform post go-live monitoring. Verify: | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | 11/04/2026 22:30:00 - 12/04/2026 18:00 | If any check fails, escalate immediately to nxzen Project Team.
(1) eWAY is delivering D0010/D0150 files to /dstage/projects/MAVIS_PROD/inbox_gaw.
(2) During DataStage staging, trigger file appears in /dstage/projects/MAVIS_PROD/gaw_file_trigger.
(3) After staging completes, GoAnywhere deletes the trigger file from /dstage/projects/MAVIS_PROD/gaw_file_trigger.
(4) Other DTC files are successfully procesed by Datastage as before
33 | Request Control-M to release Application load job | nxzen BAU | ukpnmvsprds31 | 2026-12-04 18:30
34 | Application Load kickoff -- confirm the MAVIS application load is processing staged data correctly end-to-end. | nxzen BAU | ukpnmvsprds31 | 2026-12-04 18:30
35 | Comms to Business that the staging related activities are complete and files are being staged correctly | nxzen Project Team |  | 2026-12-04 18:30
36 | Comms to Business that the staged files are processed successfully into the application tables | nxzen Project Team |  | 4/13/2026 10:00

## Rollback
MAVIS Faster Staging ¦ ROLLBACK PLAN ¦ Activate only if a critical failure cannot be resolved during the cutover window
Step # | Activity | Owner | Server / Target | Completion Date / Time | Remarks
STEP 1 -- ROLLBACK DECISION ¦ Triggered when a critical failure cannot be resolved within the agreed cutover window
RB-1 | Rollback decision: Project lead and BAU team agree that the issue cannot be resolved within the cutover window and a rollback is required. Document the reason for rollback, the step at which the failure occurred, and the time of decision. | nxzen Project Team Lead | -- | As required | This step gates all subsequent rollback steps. Do not proceed with rollback until a formal decision is made and communicated.
STEP 2 -- COMMUNICATIONS
RB-2 | Notify business stakeholders (Peter Waymont / Neal Medley / Sinida) and management that a rollback has been initiated. Provide the reason, current status, and estimated time to restore normal service. | nxzen Project Team | -- | As required | Send communication via email. Keep stakeholders updated at regular intervals during the rollback.
STEP 3 -- STOP NEW PROCESSING ¦ Prevent any further activity on the new pipeline before reverting
RB-3 | Stop all active GoAnywhere jobs immediately to prevent any further D0010 and D0150 files being picked up and processed by the new pipeline. | nxzen Project Team + nxzen BAU | 10.2.100.4, 10.2.100.5, 10.2.102.4 | As required | Confirm all GoAnywhere jobs are in stopped state before proceeding.
RB-4 | Request Control-M to put the MAVIS eWAY adapter job back on hold to prevent new D0010 and D0150 files being delivered to any folder during the rollback window. | nxzen BAU | ukpnmvsprds31 | As required | Obtain acknowledgement from Control-M team.
STEP 4 -- REVERSE FILE MOVEMENTS ¦ Move files back to original folder so DataStage can process them
RB-5 | Move any D0010 and D0150 files currently sitting in /dstage/projects/MAVIS_PROD/inbox_gaw back to the original DataStage inbox folder (inbox/DTC). This ensures no files are lost and DataStage can process them once restored. | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | As required | Check for files in inbox_gaw that have not yet been processed. Move all unprocessed files. Confirm inbox_gaw is empty after the move.
RB-6 | Check the /dstage/projects/MAVIS_PROD/gaw_file_trigger folder and remove any residual trigger files to prevent DataStage or GoAnywhere from acting on stale triggers after rollback. | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | As required | Confirm gaw_file_trigger folder is empty before proceeding.
STEP 5 -- REVERT eWAY ¦ Restore pre-cutover .ear files so eWAY delivers D0010/D0150 back to the original DataStage inbox
RB-7 | Restore the original .ear files on both eWAY production servers from the backup taken in cutover Step 20. This reverts the JMS queue configuration and eWAY will resume delivering D0010 and D0150 files to the original DataStage inbox (inbox/DTC) instead of inbox_gaw. | nxzen Project Team + nxzen BAU | UKPNIMIBXPRMQ31, UKPNIMIBXPRMQ32 | As required | Use backup taken at cutover Step 20. Apply to both servers.
RB-8 | Restart both eWAY servers to ensure the restored .ear files take full effect. | nxzen Project Team + nxzen BAU | UKPNIMIBXPRMQ31, UKPNIMIBXPRMQ32 | As required | Coordinate restart to avoid simultaneous downtime on both nodes.
RB-9 | Validate MAVIS subscriptions and confirm all applications and adapters are running correctly after the .ear restore. | nxzen Project Team + nxzen BAU | UKPNIMIBXPRMQ31, UKPNIMIBXPRMQ32 | As required
RB-10 | Confirm eWAY is now delivering D0010 and D0150 files back to the original DataStage inbox (inbox/DTC). Verify no files are being routed to inbox_gaw. | nxzen Project Team + nxzen BAU | UKPNIMIBXPRMQ31, UKPNIMIBXPRMQ32 | As required | Check eWAY routing configuration and confirm inbox/DTC is receiving files.
STEP 6 -- REVERT DATASTAGE ¦ Restore original DataStage jobs from backup
RB-11 | Restore all impacted DataStage jobs from the backup taken in cutover Step 15. This reverts the jobs to their pre-cutover state, removing the inbox_gaw routing and trigger file logic. | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | As required | Use backup taken at cutover Step 15.
RB-12 | Compile all restored DataStage jobs. | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | As required
RB-13 | Verify all restored DataStage jobs are in compiled state with no compile errors. | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | As required | Do not proceed until all jobs are confirmed compiled.
STEP 7 -- REVERT DATABASE ¦ Remove new objects and restore data if affected
RB-14 | Drop or invalidate the new database packages deployed during cutover: PKG_DTC_VALIDATION, PKG_DTC_D0010, PKG_DTC_D0150. Also revert any DDL changes made to MDQ_ETL_VALIDATION_CONFIG, MDQ_ETL_ERROR and MDQ_ETL_FILE. | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | As required | Confirm which cutover DB steps completed before the failure (Steps 10-14) and revert only those that were applied.
RB-15 | If any staging table data (STAGE_D0010_* or STAGE_D0150_* tables) was inserted or modified by the new pipeline during the cutover window, restore the affected tables from the backup taken in cutover Step 9. | nxzen DBA | ukpnmvsprdb31 | As required | Only required if the new GoAnywhere / stored procedure pipeline successfully staged any data before the failure. Confirm with the team before restoring.
RB-16 | Verify the database is back to its pre-cutover state. Run a query against USER_OBJECTS to confirm no INVALID or unexpected objects remain. Check MDQ_APP_MSG_REF and MDQ_ETL_VALIDATION_CONFIG for any spurious rows inserted during cutover. | nxzen Project Team + nxzen BAU | ukpnmvsprdb31 | As required | Run the pre-cutover baseline object count query if available.
STEP 8 -- RESUME NORMAL OPERATIONS ¦ Re-enable Control-M jobs and verify legacy pipeline is working
RB-17 | Request Control-M to release the MAVIS eWAY adapter job so that eWAY resumes delivering files to the DataStage inbox. | nxzen BAU | ukpnmvsprds31 | As required
RB-18 | Request Control-M to release the Sunday staging job so that DataStage resumes normal scheduled staging of all D-Flow files. | nxzen BAU | ukpnmvsprds31 | As required
RB-19 | Trigger the DataStage staging job manually using the backend script to process any D0010 and D0150 files that arrived during the cutover window and are now sitting in inbox/DTC. | nxzen BAU | ukpnmvsprds31 | As required | Repeat as per current BAU process until the backlog is cleared.
RB-20 | Perform post-rollback verification. Confirm: (1) eWAY is delivering D0010/D0150 files to inbox/DTC. (2) DataStage is picking up and staging files successfully. (3) MDQ_ETL_FILE, MDQ_ETL_AUDIT and MDQ_ETL_ERROR tables are being populated correctly. (4) No files are orphaned in inbox_gaw or gaw_file_trigger. | nxzen Project Team + nxzen BAU | ukpnmvsprds31 | As required | Monitor for at least 30 minutes after DataStage job completes to confirm stable operation.
STEP 9 -- POST-ROLLBACK ACTIONS
RB-21 | Communicate rollback completion to business stakeholders (Peter Waymont / Neal Medley / Sinida). Confirm that normal service has been restored and provide an estimate for when the next cutover attempt will be scheduled. | nxzen Project Team | -- | As required | Send update via email to the same distribution list used for the original cutover comms.
RB-22 | Raise an incident/change record documenting: the step at which the failure occurred, the root cause, the rollback actions taken, the time to restore, and the lessons learned. Use this to inform the next cutover attempt. | nxzen Project Team | -- | As required
RB-23 | Agree the next available cutover window with business stakeholders and the project team. Ensure root cause is resolved and tested in non-prod before scheduling the next attempt. | nxzen Project Team | -- | As required